## KCC Power Reliability & Cost Optimization — Board Summary

Prepared for GLO Trustees – October 2025

### Context

- KCC must have consistent, affordable power.

- Current supply mix: REGIDESO (public utility, 399 Fbu / kWh ≈ $0.07) and a 275 kVA generator ($0.60 – $0.70 / kWh).

- Outages and fuel prices make generator use the largest operating cost.

- Batteries and solar have higher upfront costs but can cut monthly spending and stabilize operations.

### Current Understanding

| Power Source | Typical Cost | Strength | Weakness |
| --- | --- | --- | --- |
| REGIDESO | $0.07 / kWh | Cheapest, reliable when on | Frequent outages, likely tariff increase |
| Generator | $0.60 / kWh | Always available | Extremely costly, fuel logistics, noise |
| Solar + Battery | $0.13 – $0.15 / kWh (5-yr basis) | Lowest long-term cost, scalable | Higher upfront capex |

KCC uses about 2,100 kWh/day (≈ 63 MWh/month).

Fuel and grid data need confirmation to refine numbers.

### Key Findings from Model

| Scenario | Monthly Cost (USD) | Comment |
| --- | --- | --- |
| 100 % REGIDESO | $4 k | Ideal but unrealistic (outages) |
| 21 h grid / 3 h generator | $9.5 k | Works only if outages < 3 h/day |
| 21 h grid / 3 h batteries | $6 k | Saves ≈ $3.5 k / mo vs. generator |
| 18 h grid / 6 h generator | $14 k | Fuel heavy |
| 18 h grid / 6 h batteries | $7 k | Half the cost of diesel |
| 12 h grid / 12 h generator | $23 k | Unsustainable |
| 12 h grid / 12 h batteries | $9 k | Two-thirds cheaper |
| 6 h grid / 18 h generator | $32 k | Impractical |
| 6 h grid / 18 h batteries + solar | $7.5 k | Near-off-grid option, stable long term |

Battery + inverter systems beat diesel in every case, even for short outages.

### Decisions Required

- Data & Verification

  - Confirm actual consumption (~2,100 kWh/day).

  - Record outage hours, generator fuel burn, and REGIDESO billing for 2 weeks.

  - Confirm / refine real cost per kWh for both sources.

  - Refine priorities and essentials

- Planning Depth

  - Quick / no-cost estimate), or

  - Professional energy audit & design (precise BOQ and long-term plan).

- Budget & Financing

  - Determine available budget or loan/grant path.

  - If interested in financing – Estimated in model at 5 years @ 10 % APR.

  - Option to phase-in batteries and later add solar—saves money immediately.

- Operational Choices

  - Define priority loads (what must stay on 24/7).

  - Consider simple start: UPS / battery backup for essentials, scale as savings prove out.

  - Goal: keep monthly power ≤ $10,000, ensuring reliability.

### Big Picture

- If REGIDESO ≥ 21 h/day, add limited batteries for outages.

- If REGIDESO 12–18 h/day, expand batteries—skip diesel except emergency.

- If REGIDESO ≤ 6–12 h/day, move toward solar + battery system (≈ $520 k capex, $8.7 k/mo over 5 yrs).

- Every hour shifted from diesel to stored or solar power reduces cost and dependency.

### Recommended Next Steps

### Discussion / Decision points for Trustees

- Data Gathering – Confirm consumption, outage hours, fuel usage, and actual REGIDESO cost (2-week log).

- Depth of Planning – Quick no-cost estimate or professional energy audit (BOQ + 10-year plan).

- Budget & Financing – Define capex limit, financing, source (grant / loan), repayment method.

- Phased Approach – Begin with battery backup for essentials, expand battery and only add solar if still needed

- Goal – Maintain reliability while keeping total monthly cost ≤ $10 k.

Authorize a formal cost-benefit proposal for the KCC Solar PV and Battery Storage Project, prepared in coordination with the GLO Partnerships team and verified by a technical adviser, for submission at the mid-November board meeting. Lead by the GLO Partnerships team (Ian, Martin, Paul C.) will assist; Martin will likely coordinate.